## Port Operation Dashboard
CEMENT LOADING
Berth | Vessel | Voyage # | Booking | Dispatch | Loaded | Balance | Progress | Stockpile | Time | Remarks |  | Deployed Equip. | Activity time
Berth 1 | BARGE JB 5 | 1 | 85000 | 41500 | 14500 | 70500 | 17.06% | 27000 | 17:12 | LOADING SLING S39 |  | CRANE 4 / FL 2 | 46270.1374
Berth 2 | JOHANNAH 7 | 5 | 65000 | 34000 | 33000 | 32000 | 50.77% | 1000 | 13:00 | UNSAFE TO LOAD / ROUGH SEA |  | 0 | 46270.3124
Berth 3 | VACANT | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0:00
Berth 4 | INFINITY 8 | 4 | 45000 | 6000 | 5000 | 40000 | 11.11% | 1000 | 16:33 | LOADING SLING S17 |  | 0 | 46270.1645
Berth 5 | LADY OF COURAGE | 7 | 25000 | 19500 | 18500 | 6500 | 74% | 1000 | 16:31 | WAITING GEO |  | 0 | 46270.1659
Berth 6 | VACANT | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0:00
Berth 7 | VACANT |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0:00
Berth 8 | LADY ARMOR | 5 | 17000 | 8000 | 6000 | 11000 | 35.29% | 2000 | 15:00 | WAITING AVAILABLE SHORECRANE |  | 0 | 46270.2291
Berth 9 | LADY OF WISDOM | 6 | 30000 | 6000 | 4000 | 26000 | 13.33% | 2000 | 17:15 | LOADING SLING B5 |  | SANNY 2 | 46270.1353
Berth 10 | NIEVES | 2 | 28000 | 24000 | 24000 | 4000 | 85.71% | 0 | 16:16 | WAITING MATERIAL |  | 0 | 46270.1763
Jetty | VACANT | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0:00
| TOTAL |  | 295000 | 139000 | 105000 | 190000 | 41.04% | 34000
ALPHA | Vessel |  | MATERIALS | DISCHARGE % |  | Balance | Progress |  | Time | Remarks |  | Deployed Equip. | Activity time
R1 | VESSEL 1 |  | COAL | 50% |  | 50% | 50% |  | 1:00 | STOP DISCHARGE |  | SDLG | 46270.8124
R2 | VESSEL 2 |  | COAL | 50% |  | 50% | 50% |  | 1:00 | STOP DISCHARGE |  | SDLG | 46270.8124
R3 | VESSEL 3 |  | COAL | 5% |  | 95% | 5% |  | 1:00 | STOP DISCHARGE |  | SDLG | 46270.8124
FOREIGN | Vessel |  | MATERIALS | DISCHARGE % |  | Balance | Progress |  | Time | Remarks |  | Deployed Equip. | Activity time
Jetty | VESSEL 4 |  | COAL | 5% |  | 95% | 5% |  | 1:00 | 0 |  | SDLG
Trucking | August | September | Daily |  | Vessel Cement Loading | [5 empty] | Cement loading Daily Production
SAFISCOR | 1054675 | 179000 | 25000 |  |  | 2025 | 2026 |  | 2025 | 2026 | 1st SHIFT | 36500
LAPU-LAPU | 220240 | 47000 | 8000 |  | January | 1513170 | 1219792 | July | 1185200 | 1137600 | 2ND SHIFT | 0
BADIE | 53080 | 9000 | 2000 |  | February | 1422330 | 1351343 | August | 1275600 | 1538975 | Total | 36500
GEO | 138080 | 23000 | 5000 |  | March | 1529850 | 1778988 | September | 1333325 | 237000 | TRUCKING (STOCKPILE)
UCES | 0 | 0 | 0 |  | April | 1655225 | 1326652 | October | 1568249 | 0 | SAFISCOR | 30000
APLUS | 41000 | 7000 | 2000 |  | May | 1526425 | 1836632 | November | 1014250 | 0 | LAPU-LAPU | 2000
FULACHE | 38000 | 6000 | 1000 |  | June | 1399850 | 1645728 | December | 1193484 | 0 | BADIE | 0
Total | 1545075 | 271000 | 43000 |  |  |  |  | Total | 16616958 | 12072710 | GEO | 2000
|  | Officer on Duty |  | Equipment Available |  | # of stevedor Per Shift |  |  |  |  | UCES | 0
| Supervisor | BERNABE,A |  | Crane | Forklift | 43 |  |  |  |  | APLUS | 0
| Checker | OBIAL,R / DALUSA,E |  | 3 | 6 | [5 empty] | FULACHE | 0
| PMC | JOAN / WILLIAM | [8 empty] | Total | 34000
2026-09-05 20:30
Formulas:
Vessel = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728>=EOMONTH(TODAY(),-2)+1)* ('[1]INPUT DATA'!$A4:A6728<=EOMONTH(TODAY(),-1))* ('[1]INPUT DATA'!$H4:H6728="SAFISCOR")* ('[1]INPUT DATA'!$N4:N6728) )
Vessel = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728>=EOMONTH(TODAY(),-2)+1)* ('[1]INPUT DATA'!$A4:A6728<=EOMONTH(TODAY(),-1))* ('[1]INPUT DATA'!$H4:H6728="lapu-lapu")* ('[1]INPUT DATA'!$N4:N6728) )
Voyage # = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728>=EOMONTH(TODAY(),-1)+1)* ('[1]INPUT DATA'!$A4:A6728<=EOMONTH(TODAY(),0))* ('[1]INPUT DATA'!$H4:H6728="SAFISCOR")* ('[1]INPUT DATA'!$N4:N6728) )
Voyage # = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728>=EOMONTH(TODAY(),-1)+1)* ('[1]INPUT DATA'!$A4:A6728<=EOMONTH(TODAY(),0))* ('[1]INPUT DATA'!$H4:H6728="LAPU-LAPU")* ('[1]INPUT DATA'!$N4:N6728) )
Booking = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728= IF(MOD(NOW(),1)<TIME(8,0,0),TODAY()-1,TODAY()))* ('[1]INPUT DATA'!$H4:H6728="SAFISCOR")* ('[1]INPUT DATA'!$N4:N6728) )
Booking = SUMPRODUCT( ('[1]INPUT DATA'!$A4:A6728= IF(MOD(NOW(),1)<TIME(8,0,0),TODAY()-1,TODAY()))* ('[1]INPUT DATA'!$H4:H6728="LAPU-LAPU")* ('[1]INPUT DATA'!$N4:N6728) )
Deployed Equip. = SUMPRODUCT( ('[1]INPUT DATA'!$Y4:Y6728= IF(MOD(NOW(),1)<TIME(8,0,0),TODAY()-1,TODAY()))* ('[1]INPUT DATA'!$Z4:Z6728=1)* ('[1]INPUT DATA'!$AA4:AA6728) )